## Sheet1
Risk Assesment
| Department Name: | Information Technology | Project Name: | Website Revamp |  |  | Date Last Updated: | 2025-12-27 | [10 empty] | Probability | Impact |  | Owners
[19 empty] | Very High | Very High |  | Project Manager
[5 empty] | Inherent Risk (Without controls) |  |  |  |  | Residual Risk (With controls) | [8 empty] | High | High |  | Business Analyst
Unique ID | Risk Description | Caused by & Consequences | Risk Owner(s) Name and Role | Probability | Impact | Risk rating | Control (s) | Control Owner (s) Name and Role | Residual Probability | Residual Impact | Residual Risk rating | [7 empty] | Medium | Medium |  | Developers
1 | Scope Creep | Lack of clear requirements; Timeline Delays, Budget Overruns | Project Manager | Medium | High | Severe | Implement a strict Change Control Process; any new features must be approved by the steering committee. | Project Manager | Low | Low | Sustainable | Risk Matrix | [6 empty] | Low | Low |  | Procurement Team
2 | Delays in hiring CSM | Recruitment challenges; Project Delays, Resource Constraints | Human Resource | Very Low | Very High | Severe | Start recruitment 4 weeks early; use a specialized technical recruiter or external agency for backup. | Human Resource | Very Low | Very Low | Sustainable | Impact |  | Very Low | Low | Medium | High | Very High | Very Low | Very Low |  | Human Resource
3 | Integration Challenges | Incompatible systems; System Downtime, Data Errors | CSM | Low | High | Severe | Conduct an API Compatibility Audit and run end-to-end testing in a "sandbox" environment before launch. | CSM | Medium | Medium | Moderate | Probability | Very High | Moderate | Severe | Severe | Critical | Critical |  |  |  | Quality Analyst
4 | Data Migration Issues | Manual transfer, technical errors; Data Loss, Corruption | CSM | Medium | High | Severe | Perform Automated Data Validation scripts and maintain a full backup of the legacy database. | CSM | Low | Medium | Moderate |  | High | Sustainable | Moderate | Severe | Critical | Critical |  |  |  | Subject Matter Expert
5 | Security Vulnerabilities | Coding flaws, outdated software; Data Breach, Reputational Damage | Developers | Low | High | Severe | Schedule Penetration Testing and implement SSL encryption and multi-factor authentication (MFA). | Developers | Low | Low | Sustainable |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical |  |  |  | CSM
6 | Regulatory Non-Compliance | Evolving laws, oversight; Legal Penalties, Fines | Business Analyst | Very Low | High | Moderate | Regulatory Non-Compliance ¦ Conduct a GDPR/Compliance Audit of the new site structure before moving to production. | Business Analyst | Very Low | Low | Sustainable |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical
7 | User Adoption Issues | Inadequate training, resistance; Low Engagement, Support Overload | Subject Matter Expert | Very Low | High | Moderate | Develop a Change Management Plan including video tutorials and a 2-week "Beta" testing phase for users. | Subject Matter Expert | Very Low | Low | Sustainable |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe
8 | Software License Delays | Slow procurement approval or budget disputes. Consequence: Dev team cannot use tools, leading to idle staff and missed milestones. | Procurement Team | High | Very High | Critical | Submit Purchase Requisitions in Month 1; maintain a "Critical Path" tracker for all 3rd party vendor approvals. | Procurement Team | Medium | High | Severe
[12 empty] | Inherent Risk (Without controls) | [7 empty] | Residual Risk (With controls)
[12 empty] | Impact |  | Very Low | Low | Medium | High | Very High |  | Impact |  | Very Low | Low | Medium | High | Very High
[12 empty] | Probability | Very High | [6 empty] | Probability | Very High
[13 empty] | High |  |  |  |  | 1 |  |  | High
[13 empty] | Medium |  |  |  | 2 |  |  |  | Medium |  |  | 1 | 1
[13 empty] | Low |  |  |  | 2 |  |  |  | Low |  | 2 | 1
[13 empty] | Very Low |  |  |  | 2 | 1 |  |  | Very Low | 1 | 2