## Sheet1
Risk Assesment
| Department Name: | Information Technology | Project Name: | TechCorp Cloud Migration |  |  | Date Last Updated: | 2026-01-10 | [10 empty] | Probability | Impact |  | Owners
[19 empty] | Very High | Very High |  | Application Owners
[5 empty] | Inherent Risk (Without controls) |  |  |  |  | Residual Risk (With controls) | [8 empty] | High | High |  | Security Specialists
Unique ID | Risk Description | Caused by & Consequences | Risk Owner(s) Name and Role | Probability | Impact | Risk rating | Control (s) | Control Owner (s) Name and Role | Residual Probability | Residual Impact | Residual Risk rating | [7 empty] | Medium | Medium |  | Project Manager (Owais)
1 | Application Incompatibility | Legacy apps may not function correctly in the cloud | Application Owners | High | High | Critical | Perform "Proof of Concept" (PoC) testing for the 10 critical apps early | Application Owners | Low | Medium | Moderate | Risk Matrix | [6 empty] | Low | Low |  | Network Engineers
2 | Data Security Breaches | Sensitive data exposure during transfer | Security Specialists | Low | Very High | Critical | Use encrypted tunnels and audit cloud security configurations | Security Specialists | Medium | Medium | Moderate | Impact |  | Very Low | Low | Medium | High | Very High | Very Low | Very Low |  | Cloud Architects
3 | Unexpected Downtime | Migration exceeds scheduled maintenance windows | Project Manager (Owais) | Medium | High | Severe | Schedule migrations during off-peak hours with a verified roll-back plan | Project Manager (Owais) | Very High | Very Low | Moderate | Probability | Very High | Moderate | Severe | Severe | Critical | Critical |  |  |  | IT Director
4 | Budget Overruns | Costs exceed infrastructure or contingency limits | Project Sponsor (Mikel) | Medium | Medium | Moderate | Implement real-time cost monitoring for cloud storage and networking | Project Sponsor (Mikel) | Low | Low | Sustainable |  | High | Sustainable | Moderate | Severe | Critical | Critical |  |  |  | Department Heads
5 | Resource Constraints | Key personnel like Cloud Architects are unavailable | IT Director | Medium | High | Severe | Secure formal time commitments from Department Heads and Application Owners | IT Director | Low | Medium | Moderate |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical |  |  |  | Project Sponsor (Mikel)
6 | Scope Creep | Migration of legacy systems not identified as critical | Project Manager (Owais) | High | Medium | Severe | Enforce strict change-control to keep non-critical systems out of scope | Project Manager (Owais) | Low | Very Low | Sustainable |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical
7 | Data Loss | Corruption during migration of the 30 servers | Cloud Architects | Low | Very High | Critical | Verify full backups of all 30 servers before starting migration phases | Cloud Architects | Very Low | High | Moderate |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe
8 | Knowledge Gaps | IT Team lacks cloud expertise | IT Director | Medium | Low | Moderate | Execute the "Staff Training" deliverable early in the timeline. | IT Director | Low | Very Low | Sustainable
9 | Vendor Support Failure | Delays from providers or consultants. | Project Manager (Owais) | Low | Medium | Moderate | Establish clear SLAs and escalation paths with vendors. | Project Manager (Owais) | Very Low | Low | Sustainable | Inherent Risk (Without controls) | [7 empty] | Residual Risk (With controls)
10 | Inaccurate Assessment | Missing dependencies during planning. | Cloud Architects | Medium | Medium | Moderate | Use discovery tools to map infrastructure dependencies. | Cloud Architects | Low | Low | Sustainable | Impact |  | Very Low | Low | Medium | High | Very High |  | Impact |  | Very Low | Low | Medium | High | Very High
11 | Compliance Violations | Data residency or privacy conflicts. | Department Heads | Low | High | Severe | Review data sensitivity for the 10 critical apps. | Department Heads | Very Low | Medium | Sustainable | Probability | Very High | [6 empty] | Probability | Very High | 1
12 | Underestimated Labor | $250k labor budget is insufficient. | Project Manager (Owais) | Medium | Medium | Moderate | Track labor hours weekly to identify early variances. | Project Manager (Owais) | Low | Very Low | Sustainable |  | High |  |  | 1 | 1 |  |  |  | High
13 | Network Latency | Performance issues post-migration. | Network Engineers | Medium | Medium | Moderate | Conduct performance testing on cloud networking before cutover. | Network Engineers | Low | Low | Sustainable |  | Medium |  | 1 | 5 | 2 |  |  |  | Medium |  |  | 1
14 | Inadequate Disaster Recovery | Failure to configure cloud DR. | Cloud Architects | Low | High | Severe | Test disaster recovery failover as part of the validation phase. | Cloud Architects | Low | Medium | Moderate |  | Low |  |  | 1 | 2 | 2 |  |  | Low | 3 | 4 | 3
15 | Availability of Key Personnel | Team turnover or illness. | Project Manager (Owais) | Medium | Medium | Moderate | Cross-train team members and document all migration steps | Project Manager (Owais) | Low | Low | Sustainable |  | Very Low | [7 empty] | Very Low |  | 1 | 1 | 1